## 19Jan-Mar
Pro-A |  | GIS Expert (Eiji MATSUZAKI)
Pro-B |  | GIS Expert 1 (Mike L. CAUAN)
Pro-B GIS Engineer 1 (To be Named)
|  |  |  | Jan. |  |  |  | Feb. |  |  |  | Mar. |  |  |  | Apr.
|  |  |  | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w | 1w | 2w | 3w | 4w
GIS System SetUp
Output: Complete System Setup
Enlist Software & Hardware items (specs) | bar: Jan. 1w to Jan. 3w
Finalize detailed specs for setup | bar: Jan. 2w to Jan. 3w
Start to purchase software & hardware | bar: Jan. 3w to Feb. 1w
System Set-up | bar: Feb. 2w to Feb. 3w
Test Run | bar: Feb. 4w
Data transfer from DD Team | bar: Mar. 1w
Regular operations | bar: Mar. 1w to Mar. 4w
3.13 Site Preparation Works
Utility Relocation
Output: Prepare Utility Maps Affected
Obtain Utility Data
Obtain Spatial Data on New Construction Area
Store Utility Data in Shared Folder Defined
Add Utility Data & New Construction Area to ArcGIS
Identify Affected Utility Lines Crossing & Falling within ROW
Create Utility Maps
Tree Cutting & Relocation
Output: Prepare Maps of Subect Trees to Be Cut & Relocated
Identify & Obtain Location of Subject Trees
Identify & Obtain Relocation Site of Subject Trees
Create Maps of Subject Trees & Relocation Sites
Civil Work
Output: Obtain Relevant Data & Complete GIS Setup for Civil Tasks
Identify major tasks with DOTr | bar: Jan. 1w
Identify & obtain data from DD Team | bar: Jan. 1w to Jan. 2w
Task 1
Task 2
Task 3
Task 4
Task 5
Site Preparation Work
Output: Assist Site Prep. Work, Move forward Tree Cutting Operations
Tree Inventory Survey [JDT]
Survey
Charting/Mapping
Consent/Waiver from Private land owners (DOTr)
Internal Validation
DENR Validation & Processing of Permit
Earth Balling & Transplanting [DOTr]
Determine Relocation Site
Bidding of Cutting Contractor